## Sheet1
Annex 3
TIME SCHEDULE
| N0 | ACTIVITY | NOV | DEC | JAN |  |  | FEB |  |  | MAR |  |  | APR |  |  | MAY |  |  | JUN |  |  | JUL
[5 empty] | 1 - 10 | 11 - 20 | 21 - 31 | 1 - 10 | 11 - 20 | 21 - 29 | 1 - 10 | 11 - 20 | 21 - 31 | 1 - 10 | 11 - 20 | 21 - 30 | 1 - 10 | 11 - 20 | 21 - 31 | 1 - 10 | 11 - 20 | 21 - 30 | 1 - 10 | 11 - 20 | 21 - 31
| A | PROPOSAL ACTIVITY
| 1 | Request for proposal | 27
| 2 | Proposal due |  | 15
| 3 | Award date |  | 20
| 4 | Contract start date |  |  |  | 11
| B | CONTRACT ACTIVITY
St 1 | 1 | Technical description
St 2 | 2 | Expropriation of land and property Design
| 3 | Expropriation of land
| 4 | Public discussions on Environmental impact
| 5 | Environmental impact assessment
| 6 | Public viewing Environmental assessment
| 7 | Geotechnical research
| 8 | Geodesic recordings
| 9 | Conceptual design
St 3 | 10 | Preliminary design with Feasibility Study
| 11 | State Revision of Preliminary design
St 4 | 12 | Design for Building permit
St 5 | 13 | Detail Design for execution
Beneficiary's obligation
CONCLUSION : ALL DURATION AND DEADLINES HAVE TO BE CALCULATED BY EFFECTIVELY TIME , RESPECTIVELY WHEN ALL NECESSARY CONDITIONS IS FULLFILED BY ALL PARTICIPANTS IN THIS PROJECT