## Landslides
Remediation up to 45 critical landslides affecting the road network damaged by flooding or rains
LOTs and their respective completion of the works date
Road no | ID | Section/Contracts | km | Municipality | Procurement Status | LOT | End Date
IB 30 | 1200 | Ivanjica - Ušće | 6+920,54 - 6+982,04 | Ivanjica | Contracted | Lot 1 | 2016-09-28
IB 30 | 1201 | Ivanjica - Ušće | 21+809,19 - 21+887,68 | Ivanjica
IB 29 | 1416 | Novi Pazar - Sjenica | 361+150 | Sjenica
IB 28 | 1006 | Rogačica - Užice | 119+545 - 119+595 | Užice | Contracted | Lot 2 | 2016-12-31
IB 28 | 1007 | Rogačica - Užice | 117+045 - 117+095 | Užice
IB 28 | 1008 | Rogačica - Užice | 111+745 - 111+825 | Bajina Bašta
IB 28 | 1011 | Rogačica - Kostojevići | 64+369 - 64+419 | Bajina Bašta
IB 28 | 1013 | Rogačica -Bajna bašta- Pantina Vodenica | 58+269 - 58+419 | Bajina Bašta |  |  | 2017-08-30
IB 28 | 1024 | Mokra Gora - Kremna | 501+050 - 501+138 | Užice |  |  | 2016-12-31
IIA 171 | 1025 | Bajina Bašta - Dub | 104+854 do 104+954 | Bajna Bašta
IIA 150 | 0048 | Belanovica - Aranđelovac | 83+150 - 83+180 | Gornji Milanovac | Contracted | Lot 3 | 2017-05-30
IIA 150 | 0047 | Belanovica - Aranđelovac | 82+900 до 82+943 | Gornji Milanovac
IIA 150 | 0043 | Aranđelovac-Ranilovići (Misača) | 57+340 | Aranđelovac
IIA 177 | 1111 | Sastavci - Šiljkovica | 106+000 - 106+030 | Požega
IIB 358 | 0102 | Kadina Luka - Ba - Srasle Bukve | 7+621-8+070 9+114-9+327 | Ljig
IIB 364 | 0122 | Brajkovac - Belanovica, Belanovica - Varnice, Varnice - Rudnik | 44+550 | Gornji Milanovac |  |  | 2017-01-15
IIB 364 | 0123 | Brajkovac - Belanovica, Belanovica - Varnice, Varnice - Rudnik | 44+700 | Gornji Milanovac
IIB 364 | 0124 | Brajkovac - Belanovica, Belanovica - Varnice, Varnice - Rudnik | 45+600 | Gornji Milanovac
IIB 364 | 0111 | Brajkovac - Belanovica, Belanovica - Varnice, Varnice - Rudnik | 31+600 | Belanovica
IIB 359 | 1307 | Beršići - Gornji Branjani | 7+115 | Gornji Milanovac |  |  | 2017-05-30
IB 24 | NK 1 | Ravni Gaj - Kraljevo‚Balosava 3 | 48+970 - 49+197 | Knić | Contracted | Lot 4 | 2016-09-28
IB 24 | NK 2 | Ravni Gaj - Kraljevo Balosava 4 | 49+550 - 49+775 | Knić
IIA-183 | NK 3 | Kragujevac - Donja Sabanta | 9+500 | Kragujevac
IIA 137 | 3587 | Šabac - Krupanj - Mačkov Kamen - Gračanica, deonica Krupanj - Mačkov Kamen | 2+900 | Krupanj | Contracted | Lot 5 | 2016-12-31
IIA 137 | 3588 | Šabac - Krupanj - Mačkov Kamen - Gračanica, deonica Krupanj - Mačkov Kamen | 4+400 | Krupanj
IIA 137 | 3589 | Šabac - Krupanj - Mačkov Kamen - Gračanica, deonica Krupanj - Mačkov Kamen | 5+700 | Krupanj
IIA 137 | 3590 | Šabac - Krupanj - Mačkov Kamen - Gračanica, deonica Krupanj - Mačkov Kamen | 6+100 | Krupanj
IIA 137 | 3667 | Šabac - Krupanj - Mačkov Kamen - Gračanica, deonica Krupanj - Mačkov Kamen | 3+600 | Krupanj
IIA 141 | NV 2 | Pecka - Ljubovija | 5+230 - 5+250 | Osečina
IIA 141 | 3591 | Pecka - Ljubovija | 4+500 - 4+565 | Osečina
IIA 141 | 3592 | Pecka - Ljubovija | 5+690 - 5+780 | Osečina
IIA 141 | 3593 | Crniljevo - Osečina | 10+700 - 10+740 | Osečina
IIA 141 | 3677 | Pecka - Ljubovija | 8+950 до 9+050 | Ljubovija
IB 21 | 3687 | Koceljeva - Valjevo | 116+950 | Koceljeva | Tendering in process. The contracting procedure will be completed by end August 2016. Dead lin for the completion of the works 120 days | Lot 6-1 | 2017-01-30
IIA 141 | NV 3 | Ub - Koceljeva | 40+400 | Ub
IIA 175 | 3600 | Bogdanovića Brdo - Divčibare | 35+880 - 35+900 | Mionica
IIA 175 | 3601 | Bogdanovića Brdo - Divčibare | 39+410 - 39+450 | Mionica
IIA 175 | 3602 | Bogdanovića Brdo - Divčibare | 30+250 - 30+320 | Mionica
IIA 143 | 3704 | Pričević - Pecka | 16+905 - 17+025 | Osečina | Tendering in process. The contracting procedure will be completed by mid September. Dead lin for the completion of the works 100 days | Lot 6-2 | 2017-01-30
IIA 170 | 3679 | Valjevo - Debelo Brdo - Rogačica - Bajina Bašta | 35+500 | Valjevo
IIA 170 | 3732 | Sedlare - Debelo brdo | 14+978 - 14+960 | Valjevo | Tendering in process. The contracting procedure will be completed by mid September. Dead lin for the completion of the works 100 days | Lot 6-3 | 2017-01-30
IIA 170 | 3733 | Sedlare - Debelo brdo | 22+130 - 22+150 | Valjevo
IIA 170 | 3734 | Sedlare - Debelo brdo | 22+190 - 22+208 | Valjevo
IB 24 | 3595 | Straza - Boljevac | 782+350 | Boljevac | Contracted | Lot 7 | 2016-09-18
IIA 228 | 0826 | Gornji Gajtan - Gazdare | 124+410 - 124+440 | Medveđa |  | Lot 8 | 2017-05-30
TOTAL LANDSLIDES

## Bridges
Reconstruction of up to 14 road structures (bridges, retaining walls) damaged by flooding or rains
LOTs and their respective completion of the works date
Road no | ID | Section | km | Municipality | LOT | End Date
IБ - 21 | ID2728 | Požega - Kosjerić - Valjevo, Most na pesku, reka Dobrinjska. Rehabilitacija | 188+691 do 188-722 | Kosjerić | LOT 1B | 2017-01-31
IБ - 28 | ID2710 | Dub - Okletac, projekat potpornih zidova I regulacije rečnog korita I izvođenje radova | 118+680 | Bajina Basta | LOT 1B
IБ - 21 | ID2618 | Šabac - Užička Požega, Most preko reke Dobrave, Rehabilitacija | 8+652 | Kosjerić | LOT 1B
IВ - 28 | ID2711 | Dub - Okletac, projekat potpornih zidova I regulacije rečnog korita I izvođenje radova | 119+410 | Bajina Basta | LOT 1B
IIA - 137 | ID2532 | Mojković - Krupanj, most preko reke Likodre | 0+203 | Krupanj | LOT 2B | 2016-12-31
IВ - 21 | ID2622 | Gradski most preko reke Tamnave u Koceljevi. Rehabilitacija | Koceljeva centar | Koceljeva | LOT 2B
IIA - 137 | ID2518 | Šabac - Zavlaka, Most preko reke Dumače, Rehabilitacija | 11+827 | Šabac | LOT 2B
IВ35 | NN2 | Kladovo - Zaječar - Niš, Most preko Trgoviškog Timoka | 156+807 | Knjazevac | LOT 3Ba | 2016-12-31
IВ40 | NN1 | Vladičin Han - Surdulica - Državna granica sa Bugarskom, Most preko reke Dubnice kod sela Zaglužane - projekat rekonstrukcije | 5+633,91 | Surdulica | LOT 3Bb | 2017-11-30
IIA129 | NV4 | Most Farkaždin - Kovačica, ID MOSTA: 25009 (15017,15018,15019) | 156+807 | Kovačica | LOT 4 | 2016-12-31
IIA - 174 | ID2702 | Kostojić - Varda, Projekat izgradnje novog mosta preko reke Rogačice I Regulacija rečnog korita | 1+090 | Bajina Basta | LOT 5Ba | 2017-11-30
IIA - 137 | ID2524 | Šabac - Zavlaka, Most preko reke Cernice, Srušen most, Izgradnja | 2+189 | Loznica | LOT 5Ba
IIA - 175 | ID2629 | Selo Donja Toplica Most preko reke Toplice Izgradnja novog mosta | 12+083 | Mionica | LOT 5Bb | 2017-11-30
IIA217 | NSB1 | Bukanja - Aleksinac - Soko Banja, Most preko Žitkovačke bare | 26+240 | Aleksinac | LOT 5Bb
TOTAL BRIDGES